## Slide 1: ODG Update BMC AGM 2019

## Slide 2: Overview
51 Recommendations were broken into 8 work streams:
ODG
Board Led Workstream Group
(CEO)
Member/NC Led Workstream Group
(President)
1: Strategy and Vision
(Dave Turnbull)
2: Ops and Finance
(David Lanceley)
3: Culture, Leadership and Management
(Gareth Pierce)
4: Corporate Structure
(various subgroups)
5: Governance
(Andy Syme)
6: Policy
(In planning)
7: Partnerships
(Fiona Sanders)
8: Membership Engagement
(Paul Evans)
First priority has been changes needed by AGM 2019
Second priority starting the longer running pieces of work - potential new subsidiaries
Strategy work initiated today and Culture, Leadership and Management follows immediately afterwards
Aim is to have all recommendations made to Board by AGM 2020

## Slide 3: Work Streams 1 to 4 - CEO led
Completed
Representative body for Mountaineers and governing body for competition climbing; Remain a not-for-profit Company Limited by Guarantee, following review and amendment of governance structure
Started
Strategy, vision, mission and values review
Competitions and Wales reviews
Starting after AGM 19
Culture, leadership and management review; Digital Strategy
Starting later in 2019
Existing charitable subsidiary review, and commercial activities
R1 | R21
R4 | R5
R6 | R7
R10 | R13
R14 | R20
R11 | R16
R41 | R42
R44 | R45
R24 | R25
R46 | R47
R48 | R49
R50 | R51
R22 | R23
R2 | R3
R43
R17

## Slide 4: Work Streams 5 to 8 - President led
Completed
Restructure Board, agree MoU, appoint Chair
Updates to Articles
Started
National Council Reconstitution; Membership Engagement; Clubs and Partners review; Legal Strategy
Starting after AGM 19
Specialist Committee and Policy review
Starting later in 2019
R26 | R27
R29 | R34
R39
R28 | R30
R31 | R33
R35 | R37
R12 | R15
R38 | R40
R18 | R19
R8 | R9
R32 | R36
Notes: Focus has been on Governance work ahead of AGM 19. A considerable amount of time and effort has gone into bringing the AoAs up to date, reconstituting the Board, recruiting a Chair, producing an MoU between the Board and the NC.

## Slide 5: Summary and Next Steps
By Dec 19 NC:
Membership Engagement work being implemented
Competitions, Wales, Partners and Clubs Working Groups all reported to Board
All work underway or complete
By AGM 2020:
All recommendations made to the Board of Directors
R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8
R9 | R10 | R11 | R12 | R13 | R14 | R15 | R16
R17 | R18 | R19 | R20 | R21 | R22 | R23 | R24
R25 | R26 | R27 | R28 | R29 | R30 | R31 | R32
R33 | R34 | R35 | R36 | R37 | R38 | R39 | R40
R41 | R42 | R43 | R44 | R45 | R46 | R47 | R48
R49 | R50 | R51 |  |  |  |  | 
White: Complete
Green: Started and progressing to plan
Amber: Planned to start immediately after AGM 19
Red: Planned to start later in 2019
Summary by Recommendation:

## Slide 6: Feedback
Please feel free to ask any questions or mail them in to
odg@thebmc.co.uk
Finally, a huge thank you to the significant number of BMC volunteers and staff that have collectively put thousands of hours of work into the ODG